Project planner uses periods for intervals. Start=1 is period 1 and duration=5 means project spans 5 periods starting from start period. Enter data starting in B5 to update the chart
Title of the project. Enter a new title in this cell. Highlight a period in H2. Chart legend is in J2 to AI2
Select a period to highlight in H2. A Chart legend is in J2 to AI2
Enter activity in column B, starting with cell B5
Enter plan start period in column C, starting with cell C5
Enter plan duration period in column D, starting with cell D5
Enter actual start period in column E, starting with cell E5
Enter actual duration period in column F, starting with cell F5
Enter the percentage of project completed in column G, starting with cell G5
Enter a period in the range of 1 to 60 or select a period from the list. Press ALT+DOWN ARROW to navigate the list, then ENTER to select a value
Type a value from 1 to 60 or select a period from the list-press CANCEL, ALT+DOWN ARROW, then ENTER to select a value
Periods are charted from 1 to 60 starting from cell H4 to cell BO4
This legend cell indicates plan duration
This legend cell indicates actual duration
This legend cell indicates the percentage of project completed
This legend cell indicates actual duration beyond plan
This legend cell indicates the percentage of project completed beyond plan
## Project Planner
Real-time C++ OFDM
Select a period to highlight at right. A legend describing the charting follows.					Period Highlight:	1			Plan Duration					Actual Start					% Complete					Actual (beyond plan)					% Complete (beyond plan)
ACTIVITY	PLAN START	PLAN DURATION	ACTUAL START	ACTUAL DURATION	PERCENT COMPLETE	Days (Start 14/06/2021, Planned Finish 03/08/2021)
					1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52	53	54	55	56	57	58	59	60
Prelim Report	1	5	1	4	80%
Specification	1	35	1	4	70%
Project Framework	1	5	1	4	70%
TX & RX - IFFT & FFT	1	5	1	4	70%
Testing & Release v0.1	5	1	1	0	0%
Band-Pass Modulator	6	2	0	0	0%
Band-Pass Demodulator	6	2	0	0	0%
Testing & Release v0.2	8	1	0	0	0%
Cyclic Prefix Addition	9	1	0	0	0%
Coarse Symbol Start – Cross Correlation Filter	10	2	0	0	0%
Testing & Release v0.3	12	1	0	0	0%
Tx - Pilot Tone Addition	13	1	0	0	0%
Rx - Pilot Tone Search	14	1	0	0	0%
Testing & Release v0.4	15	1	0	0	0%
Tx - QAM Modulator	16	1	0	0	0%
Rx - QAM Demodulator	17	1	0	0	0%
Testing & Release v0.5	18	1	0	0	0%
Audio Driver	19	3	0	0	0%
Tx Audio	22	1	0	0	0%
Rx Audio	23	3	0	0	0%
Testing & Release v0.6	26	2	0	0	0%
Phase Error Correction	28	5	0	0	0%
Testing & Release v0.7	33	2	0	0	0%
Audio Demo	35	5	0	0	0%
Poster	40	7	0	0	0%
Report	1	50	1	0	0%